# Quickstart

- As an organizer (even if you were previously an MLOps Community Organizer), please fill in the intake form.

- READ THIS Playbook for organizers thoroughly,

- Chapter Folder can be found here. Each should contain,

  - Event Tracker (for you to keep track of events, and tasks for each)

  - Banners (for the luma and chapter pages)

  - <Event Folder>

    - Slides for the day of the event

    - Slides for banners and sharing on LinkedIn

    - [optional] Attendee CRM (To keep track and notes)

    - AI writing prompts now live as Claude skills (the AAIF meetup skills repo), not in this folder

- PLEASE UPDATE THESE FOR YOUR CHAPTER

- Luma Event to clone (please ping ijeoma to be added as organizer so that you can clone it. NOTE: this event has form to fill and a terms the attendees need to accept)

  - When you clone an event, please add AAIF Community as host so we can track the event.

  - Create a tab in your event tracker doc.

- Templates Folder (Will have latest shared templates)

- Link to share with people who want to host, speak, or become organizers. 
NOTE : Each of these has special guidelines that they need to agree to.

  - It adds to our "database" (which is a Google Sheet for now) and allows us to track, approve, and also reach out to them for future events.

  - All the guidelines for people looking to get involved are here:

    - Organizers

    - Speakser

    - Venue Hosts

    - Collaborators

    - Attendees

    - Paid Venues

How to use this tracker - One event = one section = one Google Docs tab. The example below is your starting point — copy it and edit in place. - Fill the details first. The Luma URL is the source of truth for date, time, and RSVPs. - Each phase is a table: set the Owner, a Due date, and move Status from Not started → In progress → Done. - Words, prompts, and branding assets (Day-of slides, Luma banner, LinkedIn carousel, logo) live in the shared Resources & Templates doc.

AGENTIC AI FOUNDATION · COMMUNITY SERIES

# San Francisco Chapter

Self-organizing playbook for each chapter and event

## About the AAIF SF Chapter

The AAIF San Francisco chapter serves as a vibrant hub for the local agentic AI community. We bring together developers, researchers, and builders to discuss practical implementations, share learnings from production environments, and foster collaboration on key open-source agentic AI projects. Our events prioritize hands-on demos and technical deep dives, ensuring that the San Francisco community remains at the forefront of agentic AI innovation. We also have a sister chapter - Silicon Valley.

## Local Chapter Vibes

Our events are built for builders. We prioritize signal over noise, focusing on technical deep dives, practical demos, and honest conversations about what works in production. It’s an intimate, curated, and vendor-neutral space where the community gathers to share real artifacts, solve hard problems together, and build the future of agentic AI in real time.

## Organizers

- Rahul Parundekar

- Arthur Coleman

- Leo Walker

- Shreeganesh Ramanan (SG)

## Luma & Socials

- https://luma.com/aaif-sanfrancisco

# June 24, 2026  ·  AGENTIC AI NIGHT — LAUNCH SERIES

Example event — duplicate this whole section per night and overwrite the details.

| EVENT TITLE | Agentic AI Night · Launch Series |
| --- | --- |
| DATE & TIME | Tue · June 24, 2026 · 17:30 — late |
| LOCATION / CITY | South of Market, San Francisco |
| VENUE | Host Venue Co. — SoMa (doors, A/V, F&B) |
| THEME / SERIES | Agents in production (Launch Series) |
| FORMAT(S) | Talk / Panel / Science Fair / Hackathon / Pitch Night / Workshop / Show & Tell / etc. |
| SPEAKER(S) | Maya Chen (Staff Eng · Payments); Diego Alvarez (Founding Eng · Agent Infra); Priya Nair (OSS · goose) |
| LUMA URL | lu.ma/aaif-sanfrancisco |
| CAPACITY / RSVPS | 120 · curated, RSVP-based |
| ORGANIZER ON POINT | Organizer Name (co: Organizer Name) |

4 WEEKS OUT   May 27 · lock the basics

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Confirm date, venue, and a hold on the space | Organizer | May 27 | Done |
| Decide the theme / series and capacity | Local champs | May 27 | Done |
| Confirm speakers + talk titles and one-line abstracts | Organizer | May 27 | Done |
| Draft the event description (Resources → Luma prompt) | Co-organizer | May 29 | Not started |
| Create the Luma event (draft); set cover (AAIF Luma Banners) | Co-organizer | May 29 | In progress |

3 WEEKS OUT   Jun 3 · open RSVPs & announce

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Publish the Luma event; turn on the waitlist | Co-organizer | Jun 3 | Not started |
| Finalize headshots, bios, talk titles (Resources → bio prompt) | Organizer | Jun 4 | Not started |
| Post the LinkedIn announcement + carousel | Co-organizer | Jun 4 | Not started |
| Ask speakers and venue to reshare | Organizer | Jun 5 | Not started |
| Confirm A/V with venue (HDMI / USB-C, mic, screen, sound) | Venue | Jun 6 | Not started |

2 WEEKS OUT   Jun 10 · logistics

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Confirm food & drinks order and headcount | Venue | Jun 10 | Not started |
| Assign a photographer / someone on photos | Co-organizer | Jun 10 | Not started |
| Check name tags, markers, placard supplies | Organizer | Jun 11 | Not started |
| Send reminder #1 to RSVPs (Resources → reminder prompt) | Co-organizer | Jun 11 | Not started |
| Line up a volunteer for the door / check-in | Organizer | Jun 12 | Not started |

1 WEEK OUT   Jun 17 · final prep

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Re-confirm speakers: arrival, slide format, demo / wifi needs | Organizer | Jun 17 | Not started |
| Re-confirm venue access, on-site contact, load-in time | Venue | Jun 17 | Not started |
| Finalize run-of-show / agenda with timings | Organizer | Jun 18 | Not started |
| Build the day-of slides (AAIF SF Day of Event) | Co-organizer | Jun 19 | Not started |
| Send reminder #2 + calendar add to RSVPs | Co-organizer | Jun 20 | Not started |

DAY BEFORE   Jun 23

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Print the attendee / check-in list | Organizer | Jun 23 | Not started |
| Prep name tags, markers, speaker-timings placard | Co-organizer | Jun 23 | Not started |
| Charge a phone / laptop for background music | Co-organizer | Jun 23 | Not started |
| Pack the kit: adapters, mic, extension cord, tape, Sharpies | Organizer | Jun 23 | Not started |
| Confirm who opens the space, and when | Organizer | Jun 23 | Not started |

DAY OF   Jun 24 · setup runbook

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Organizer arrives early, on point | Organizer | 16:00 | Not started |
| Drinks arrived and chilling; ice + buckets sorted | Venue | 16:30 | Not started |
| A/V connected and tested with speaker laptop | Venue | 16:45 | Not started |
| Attendee list at the door; tables cleared, room set | Organizer | 16:45 | Not started |
| Background music on; speaker-timings placard placed | Co-organizer | 17:00 | Not started |
| Food arrives, with plates and napkins | Venue | 17:15 | Not started |
| Name tags + markers out at check-in | Co-organizer | 17:20 | Not started |
| Doors & networking; photographer briefed and shooting | Everyone | 17:30 | Not started |
| Why we’re here (community intro + theme) | Organizer | 18:00 | Not started |
| Talk one — keep time with the placard | Speaker | 18:05 | Not started |
| Demos × 3 (5 min each) | Demo host | 18:30 | Not started |
| Wrap up — next event plug, photo moment | Organizer | 18:55 | Not started |
| Social pulse — open networking till late | Everyone | 19:00 | Not started |

NEXT DAY   Jun 25

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Thank speakers; collect slides to share | Organizer | Jun 25 | Not started |
| Thank the venue and any members who helped | Organizer | Jun 25 | Not started |
| Post the recap on LinkedIn with photos (Resources → recap) | Co-organizer | Jun 25 | Not started |
| Upload photos + decks to the shared drive | Co-organizer | Jun 25 | Not started |
| Note final attendance vs RSVPs | Organizer | Jun 25 | Not started |

FOLLOW-UPS   by Jun 30 · within a week

| TASK | OWNER | DUE | STATUS |
| --- | --- | --- | --- |
| Share recording / slides / demo links with attendees via Luma | Co-organizer | Jun 27 | Not started |
| Send the post-event feedback ask | Organizer | Jun 27 | Not started |
| Capture lessons learned here — what to change next time | Organizer | Jun 30 | Not started |
| Add interested attendees + speakers to the pipeline | Organizer | Jun 30 | Not started |
| Tee up the next event’s date (“AI in Finance” — Jul 22) | Local champs | Jun 30 | Not started |